## Project Planner
Christina's Project Planner
[7 empty] | Period Highlight: | 10 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY |  |  | PLAN START Days 1 - 50 OGL320 | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
OGL 320 Fall B |  |  | 1 | 2 | 1 | 1 | 25%
| Research Professor Due 7/14/2017 |  | 1 | 1 | 1 | 2
| Sign-up for best class 8/14/17 |  | 1 | 1 | 1 | 2
| Order book 8/14/17 |  | 1 | 1 | 1 | 1
|  | Receive book/Inspect | 1 | 1 | 1 | 1
| Watch for Professor's Email |  | 1 | 7 | 1 | 2 | 25%
Cylabus & Schedule |  |  | 1 | 7 | 1 | 5
| Create Schedule |  | 1 | 2 | 1 | 2
| Adjust work schedule |  | 1 | 2 | 1 | 1 | 25%
Module 1 - Planning |  |  | 1 | 7 | 1 | 6 | 100%
| Cylabus Quiz Due: 10/13/17 |  | 3 | 1 | 3 | 1 | 100%
| Read O'Connell & Wiefling Chpt 1 & 2 & Supplemental Papers |  | 1 | 7 | 1 | 5 | 100%
|  | Notes | 1 | 2 | 2 | 2 | 100%
| Mindset & Critical Thinking Chpt 1 & 2 |  | 1 | 2 | 1 | 2 | 35%
|  | Notes | 1 | 1 | 1 | 1 | 100%
| Rubric: Outline for Baseline |  | 4 | 1 | 4 | 1 | 10%
| Write Baseline Assesment 10/14/2017 |  | 4 | 2 | 3 | 1 | 85%
|  | Sight references - Check APA Format | 4 | 1 | 4 | 2 | 100%
| Submit Baseline in Discussion Due: 10/16/17 |  | 5 | 1 | 5 | 1 | 85%
|  | Assess plan: View grade rewrite for extra credit | 6 | 1 | 6 | 0 | 100%
|  | Submit Extra Credit Rewrite Baseline | 7 | 1 | 7 | 0 | 0%
| Rubric: Outline for Project Plan |  | 7 | 1 | 7 | 1 | 100%
| Write Project Plan 10/18/2017 to 10/20/2017 |  | 8 | 3 | 7 | 3 | 85%
|  | Review Rubric & Instruction videos | 9 | 1 | 9 | 1 | 100%
|  | Sight references - Check APA Format | 9 | 1 | 9 | 1 | 100%
| Submit Project Plan Due: 10/20/17 |  | 7 | 2 | 6 | 2 | 100%
|  | Assess plan: View grade rewrite for extra credit | 11 | 2 | 11 | 3 | 100%
|  | Reasses adjacent project time less 1 point credit-edit for replanning | 15 | 1 | 15 | 1 | 100%
| Submit Extra Credit Rewrite |  | 11 | 1 | 11 | 0 | 0%
Module 2 - Rubric & Quality Control 10/21 - 10/28 |  |  | 11 | 7 | 8 | 7 | 100%
| Read O'Connell & Wiefling Chpt 10 & 11 |  | 11 | 2 | 8 | 1 | 100%
|  | Notes | 11 | 2 | 11 | 3 | 100%
| View Videos and Supplimental & Take Notes |  | 11 | 2 | 8 | 1 | 100%
| Rubrics Quiz Due:10/23/17 |  | 13 | 1 | 10 | 1 | 100%
| Rubrics Discussion Due: 10/27/2017 |  | 13 | 1 | 12 | 2 | 100%
|  | Assess plan: View grade rewrite for extra credit | 14 | 1 | 15 | 2 | 100%
| Submit Extra Credit Rewrite |  | 14 | 1 | 14 | 0 | 0%
Module 3 - PM Biases |  |  | 17 | 7 | 14 | 5 | 100%
| Bias Video Quiz Due: 10/27 |  | 17 | 1 | 15 | 1 | 100%
| Biases Discussion Due: 10/27/2017 |  | 17 | 6 | 15 | 3 | 100%
|  | Assess Discussion: View grade rewrite for extra credit | 18 | 1 | 18 | 2 | 50%
| Submit Extra Credit Rewrite |  | 19 | 1 | 19 | 6 | 50%
|  | Assess Discussion extra credit score. None. An Error. Go back rewrite 11/12/2017, rubric, resubmit, view score. | 18 | 1 |  |  | 10%
Module 4 - PM Skills |  |  | 21 | 7 | 18 | 5 | 100%
| Wiefling Chpt7, 8 & 10 |  | 21+E49 | 2 | 17 | 3 | 100%
|  | Notes | 21 | 2 | 17 | 3 | 100%
| View Videos and Supplimental |  | 21 | 1 | 18 | 1 | 100%
|  | Notes | 21 | 1 | 18 | 2 | 100%
| Framing Situations Skill Video Quiz Due: 10/31/17 |  | 21 | 1 | 22 | 1 | 100%
| Critical Thinking Skill Video Quiz Due: 10/31/2017 |  | 21 | 6 | 21 | 1 | 100%
|  | Checking scores and supplimental reasses progress | 21 | 2 | 22 | 1 | 100%
| Ruberic to outline & write PM Skills Discussion |  | 21 | 1 | 20 | 2 | 100%
| PM Skills Discussion Due: 10/31/2017 |  | 21 | 2 | 20 | 3 | 100%
|  | Assess Discussion: View grade | 22 | 1 | 22 | 3 | 100%
|  | Use Rubric Rewrite Extra Credit with extra content | 22 | 2 | 22 | 0 | 100%
| Submit Extra Credit Rewrite-Full grade value recieved |  | 22 | 1 | 22 | 0 | 100%
Module 5 - Cases 1 & 2 Due: 11/04/2017 |  |  | 22 | 5 | 21 | 8 | 100%
| Read O'Connell & Wiefling Chpt 3 & 4 w/Notes |  | 22 | 2 | 21 | 2 | 100%
| Mindset Diary |  | 22 | 2 | 20 | 5 | 100%
| View Videos, Challenger and Supplimental |  | 22 | 2 | 21 | 1 | 100%
|  | Notes | 21 | 2 | 21 | 2 | 100%
| Ruberic to write Case Study Comparison |  | 22 | 2 | 21 | 1 | 100%
| Case Studies Comparison - Discussion Due: 11/3/2017 |  | 24 | 2 | 22 | 2 | 100%
|  | Assess Discussion: View grade rewrite for extra credit | 26 | 2 | 26 | 4 | 60%
| Submit Extra Credit Rewrite |  | 32 | 2 |  |  | 0%
Module 6 Re-planning |  |  | 25 | 7 | 25 | 7 | 100%
| Read O'Connell & Wiefling Chpt 4, 5 & 6 |  | 25 | 4 | 25 | 5 | 100%
|  | Notes | 26 | 2 | 25 | 2 | 100%
| View Videos and Supplimental |  | 25 | 1 | 25 | 1 | 100%
|  | Notes | 25 | 1 | 25 | 2 | 100%
| Ruberic to update project plan |  | 30 | 1 | 30 | 2 | 100%
| Update your project plan Due: 11/10/2017 |  | 31 | 1 | 31 | 1 | 100%
|  | Assess Discussion: View grade rewrite for extra credit | 32 | 2 |  |  | 0%
| Submit Extra Credit Rewrite |  | 33 | 1 |  |  | 0%
Module 7 - Case Studies 3 & 4 |  |  | 32 | 7 |  |  | 0%
| Read Wiefling Chpt 12 & 13 w/Notes |  | 32 | 4 |  |  | 0%
| View Videos and Supplimental on Case studies & Take Notes |  | 32 | 4 |  |  | 0%
| Ruberic to write Case Studies Critique |  | 36 | 2 |  |  | 0%
| Compare 2 Projects - Success & Failure Due: 11/17/2017 |  | 38 | 1 |  |  | 0%
|  | Assess Discussion: View grade rewrite for extra credit | 39 | 1 |  |  | 0%
| Submit Extra Credit Rewrite |  | 40 | 1 |  |  | 0%
Module 8 - Case Study 5 |  |  | 39 | 7 |  |  | 0%
| Read Any Supporting Material & Videos w/Notes |  | 39 | 7 |  |  | 0%
| Ruberic evaluation to write Big Dig |  | 42 | 2 |  |  | 0%
| The Big Dig Case Study - Discussion Due: 11/24/2017 |  | 45 | 1 |  |  | 0%
|  | Assess Discussion: View grade rewrite for extra credit |  | 1 |  |  | 0%
| Submit Extra Credit Rewrite |  |  | 2 |  |  | 0%
Module 9 - Culmination |  |  | 46 | 7 |  |  | 0%
| Re-Read O'Connell & Wiefling & Supporting Materials |  | 46 | 6 |  |  | 0%
| Reflect on Project |  | 46 | 6 |  |  | 0%
| Culminating Project Discussion Due: 11/29/2017 |  | 49 | 1 |  |  | 0%
|  | Assess Discussion: View grade rewrite for extra credit | 50 | 1 |  |  | 0%
| Extra Credit Post |  | 50 | 1 |  |  | 0%